## Instructions
Budget Calculator (Basic) - Foundation Tier
1) Enter or adjust low/high estimates in the Calculator tab (yellow cells).
2) Review totals and cost per square foot outputs (green cells).
3) Set a contingency between 10% and 15% unless site risk is unusually low/high.
4) Use this as an early feasibility screen, not a contractor bid substitute.

## Calculator
ADU Budget Calculator (Basic)
Category | Low Estimate ($) | High Estimate ($) | Selected Estimate ($) | Notes
Design / architecture | 12000 | 28000
Engineering (structural/civil/geotech) | 6000 | 18000
Permits and fees | 5000 | 20000
Site preparation | 8000 | 25000
Foundation | 12000 | 35000
Framing | 18000 | 45000
Roofing | 5000 | 15000
MEP rough-in | 18000 | 50000
Insulation + drywall | 7000 | 22000
Finishes (flooring/cabinets/fixtures) | 20000 | 60000
Exterior | 7000 | 20000
Utility connections | 8000 | 30000
Landscaping/hardscape | 3000 | 15000
Contingency reserve (line-item placeholder) | 10000 | 35000
Total (before contingency %)
Target ADU size (sq ft) | 800
Low $/sq ft
High $/sq ft
Selected $/sq ft
Contingency % (recommended 10%-15%) | 12%
Contingency amount (selected total)
All-in selected estimate

## Sources
Source | URL | Notes
ADU cost benchmark context (consumer range) | https://www.angi.com/articles/how-much-do-adu-costs.htm | Use for early screening only; validate with local bids.
California ADU Handbook | https://www.hcd.ca.gov/sites/default/files/docs/policy-and-research/adu-handbook-update.pdf | Legislative and process context.
Author PM experience | N/A | Category C judgment for structure and contingency logic.